## 2015 Proposed Operating Budget
2015 WWC Village Council Expense Budget - Final | 2014 Budget | 2014 Actual January-October | 2015 Proposed Budget - Elite | 2015 Proposed Budget - VC BOD
REVENUE
Common Charge Income - 72 units @ $225/unit | 194400 | 162000 | 194400 | 203040 | Increase of $10.00/month/Unit = 4.5% increase
Contribution Charge to Conservancy- 72 units @ $50/unit | 43200 | 36000 | 43200 | 43200
Sub-total Gross Revenue | 237600 | 198000 | 237600 | 246240
Revenue Adjustments
Contribution Charge to Conservancy | 43200 | 36000 | 43200 | 43200
Transfer to Reserves - 2% increase per Reserve Study advice | 34174 | 25630.47 | 34174 | 34857.48 | 2% increase per Reserve Study advice
Sub-total Revenue Adjustments | 77374 | 61630.47 | 77374 | 78057.48
Net Revenue | 160226 | 136369.53 | 160226 | 168182.52
EXPENSES
Management Fees - Elite | 8517 | 7097.5 | 8517 | 8517
Sub-total Management Fees | 8517 | 7097.5 | 8517 | 8517
Utilities
Electricity (Street Lights) | 1400 | 1144.21 | 1400 | 1400
Water and Sewer | 20000 | 18828.25 | 20000 | 20000
Sub-total Utilities | 21400 | 19972.46 | 21400 | 21400
Maintenance
Catch Basin Clean and Repair | 5000 |  | 5000 | 5000
Irrigation Repairs and Improvements | 5000 | 2850.08 | 5000 | 1500
General Maintenance and Repair | 4000 | 3735.57 | 2000 | 4000
Mailbox Repairs | 0 | 0 | 0 | 2700 | Estimate of $150 each for lower village, and $75 each for Knoll. Plan to do 25% of mailboxes/year
Walkway Repairs (Actual is combination Expense and Reserves) | 3000 | 3000 | 5000 | 0 | $15,000 Included in the 2015 Reserves
Lawn Care and Trimming (Per Contract) | 58755 | 51414.69 | 58755 | 57401 | This line item now reflects the new contract rates with RLL
Landscaping - Mulch every other year | 0 | 0 | 11600 | 11600 | This number is not included in the new RLL Lawn Care and Triming contract
Landscaping - General Improvements | 11000 | 9535.94 | 9400 | 10000 | Included in this line item is $1600.00 for Lawn Aeration and overseeding, and $1000.00 for Fence Washing
Tree Work - General Improvements | 10000 | 5167.01 | 0 | 10000
Snow Removal (Per Contract) | 30054 | 22540 | 30054 | 35595 | This line item now reflects the new contract rates with RLL
Extra Snow/Salting Services | 3500 | 4374 | 3500 | 0 | This line item is now included in the Snow Removal number
Pest Control | 0 | 265.88 | 0 | 400 | Unplanned in 2014, so included for the just icase factor
Sub-total Maintenance | 130309 | 102883.17 | 130309 | 138196
Total Expenses | 160226 | 129953.13 | 160226 | 168113
Net Income | 0 | 6416.4 | 0 | 69.52

## 2015 Proposed Reserves Budget
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
Beginning Balance on 1/1 | 74271 | 83516.48 | 88373.96 | 108928.5896 | 105194.3118 | 102185.3484 | 79916.2058
Estimated Contributions annual 2% increase) | 34174 | 34857.48 | 35554.6296 | 36265.7222 | 36991.0366 | 37730.8574 | 38485.4745
Prior Year Operating Budget Adjustment
Capital Improvements
Phase 2 Lockview Screening Project | -9928.52 | RLL Work Order Numbers 15523
Phase 3 Lockview Screening Project |  | RLL Work Order Numbers 15523
Phase 4 Lockview Screening Project |  | RLL Work Order Numbers 15523
Additional Tree Work
Sub-total Capital Improvements | -9928.52 | 0 | 0 | 0 | 0 | 0 | 0
Required Improvements Per Reserve Study
Driveways - Phase 1 Knoll |  |  |  | -40000
Driveways - Phase 2 Knoll |  |  |  |  | -40000
Road Mill and Overlay/Catch Basins | [5 empty] | -60000 | -60000
Irrigation System |  | -15000 | -15000
Light Posts
Cement Walks
Paved Walks
Fences
Stone Walls
Brick Walkways | -15000 | -15000
Sub-total Resrve Study Improvements | -15000 | -30000 | -15000 | -40000 | -40000 | -60000 | -60000
Projected Balance at EOY | 83516.48 | 88373.96 | 108928.5896 | 105194.3118 | 102185.3484 | 79916.2058 | 58401.6803

## 2014 Complete Projects
2014 Walkway Repairs - RLL WO# 12459 | 17454.03 | Status - These expenses were paid for using a combination of 2014 Budget - Reserves and Planned Capital Improvement Line Items
5 OTG |  | Complete late Spring 2014
6 OTG |  | Complete late Spring 2014
143 Pierce |  | Complete late Spring 2014
32 KWN |  | Complete late Spring 2014
38 KWN |  | Complete late Spring 2014
21 IVY |  | Complete late Spring 2014
23 IVY |  | Complete late Spring 2014
24 IVY |  | Complete late Spring 2014
41 Sagewood |  | Complete late Spring 2014
121 Heather |  | Complete late Spring 2014
146 MG |  | Complete late Spring 2014
Completed Lawn, Woodline and Landscaping Projects | 23748.57 | Status - These expenses were paid for using a combination of 2014 Operating Budget - Catch Basin Clean/Repair, Landscape Improvement and Tree Work Line Items, and Reserve Budget - Lockview Screening Work.
RLL WO#12937 - Woodline Area cleanup between 32-36 KWN | 1684.58 | Completed in Late Fall of 2013
RLL WO#12106 - Remove Common Bed behind Units 3 and 5 OTG | 671.81 | Complete on 9/15/2014
RLL WO#12109 - Remove Common Beds behind 535 and 139 Pierce | 1198.46 | Complete on 9/15/2014
RLL WO#12944 - Woodline Area cleanup between 130-136 Primrose Lane | 1684.58 | Complete on 9/22/2014
RLL WO#12945 - Woodline Area cleanup between 124 Heather and Corner Fence at 43 Sagewood | 553.02 | Complete on 9/22/2014
RLL WO#12946 - Woodline Area cleanup between the Corner Fence of 43 Sagewood to 30 KWN | 3369.17 | Complete on 9/22/2014
RLL WO#12949 - Woodline Area soften soild and plant new lawn between 136 Primrose and 30 KWN | 1532.45 | Complete on 9/22/2014
RLL WO#12667 - Core Aeration of Common Area lawns | 1616.52 | Complete on 9/19/2014
Revised RLL WO#12112 - Various landscaping projects around the units within the Village and Knoll | 1512.31 | Complete 9/24/2014 - original WO reduced by $1,000.00
RLL WO#15212 - 23 IVY replace front lawn damaged due to faulty irrigation system | 838.04 | Complete on 9/26/2014
RLL WO#15171 - 34 KWN - take-down maple, and prune tall Oak in front of house. | 1244.83 | Complete on 10/3/2014
34 KWN Walkway | 0 | Mark of RLL agreed to make small repairs to front walkway free of charge. Mark actioned on 9/25/2014 to complete the repairs
RLL WO#15429 - 342 Mercer Drainage issues | 481.77 | Complete 10/22/2014
RLL WO# 15528 - 503 and 507 Hawthorne drainage issues | 446.67 | Complete on 11/11/2014
Replace seven (7) Catch Basins located within the Knoll Community | 3800 | Work is inprocess with Central Sealing Company, Inc. This quote will be paid using $3800.00 of the $5000.00 2014 budgeted line item.
New RLL WO#15512 - Aster Place Turnaround Area | 4479.89 | Complete on 11/19/2014 - Had a meeting with HO's, agreed to resolution with HO's was to slightly move and slightly enlarge the arae, and reconstruct with like materials.
RLL WO#15501 14 Aster Place; drainage issue at the left-side of driveway, near the garage door. | 319.05 | Complete on 11/19/2014
RLL WO#15512 Sink Hole at Aster Place, behind 38 KWN |  | Complete 0n 11/19/2014, as part of RLL WO# 15523
Lockview Screening Project - RLL WO#15523, replacing WO# 14678 | 9928.52 | Complete on 11/22/2014 - New plan using RLL WO# 15523. Funding is using 2014 Reserve Budget. Reduced Original of $43,000 to $9,928.52
Quotes that were Cancelled |  | Status
RLL WO#12113 - plantings on stone grade along RH side of garage at 26 Ivy |  | Cancelled
RLL WO#12114 - reduce the size of the bed between 503 and 507 Hawthorne Lane |  | Cancelled
RLL Quote#s 15526, 14855, 15524, 14856, 14861, 10357 and 14678 |  | Cancelled all of these quotes as the work was either done under other work orders, or decided not to do the work

## Walks
# | Address |  |  | 2016
Scheduled
1 | 1 OTG |  | HARNER
2 | 3OTG | ADJOINED | DEVIZIO |  | Done 2013
3 | 5 OTG | ADJOINED | TOWERS |  | Done 2014
4 | 2 OTG |  | DEB/LARK | 1540 | 2016
5 | 4 OTG | ADJOINED | FREEMAN | 1540 | 2016
6 | 6 OTG | ADJOINED | TWARKINS |  | Done 2014
7 | 342 MER | ATTACHED | TORPEY
8 | 338 MER | ATTACHED | MUSKA
9 | 334 MER |  | MYERS
10 | 330 MER | ATTACHED | MITCHELL
11 | 503 HAW | ATTACHED | FITZGERALD | 1540 | 2016
12 | 507 HAW |  | DENKER
13 | 511 HAW |  | SMITH | 1540 | 2016
14 | 515 HAW | ADJOINED | MACALVANE
15 | 519 HAW | ADJOINED | WILLETTE
16 | 523 HAW | ADJOINED | LYONS | 1210
17 | 527 HAW | ADJOINED | MANION |  | Done 2015
18 | 531 HAW |  | NELSON
19 | 535 HAW |  | LE | 1270 | 2016
20 | 539 HAW | ATTACHED | CASAGRANDE | 2270 | 2016 | New bricks
21 | 139 PIER | ATTACHED | ABRAHAM | 3575 | 2016
22 | 143 PIER |  | CURTIS |  | Done 2014
23 | 147 PIER | ATTACHED | SIKORA
24 | 151 PIER | ATTACHED | LENNON
25 | 141 MG | ADJOINED | RAYMOND
26 | 143 MG | ADJOINED | BELL
27 | 145 MG |  | BOBBITT
28 | 146 MG | ADJOINED | COLLIER |  | Done 2014
29 | 144 MG | ADJOINED | ELLIS
30 | 142 MG |  | MUNLEY
31 | 106 KWS |  | ARMSTRONG |  | Done 2012
32 | 107 KWS | ADJOINED | HAMLET
33 | 105 KWS | ADJOINED | FIELDS
34 | 103 KWS |  | NEWELL
35 | 101KWS |  | TEFFT
36 | 131 PRIM |  | LACEY
37 | 133 PRIM |  | PISZCHALA
38 | 135 PRIM |  | DOSTAL
39 | 136 PRIM |  | SAXTON
40 | 134 PRIM |  | PALLADINO |  | Done 2015
41 | 132 PRIM |  | GELLERT |  | Done 2015
42 | 130 PRIM |  | McGOVERN
43 | 121 HEA |  | MISNER |  | Done 2014
44 | 123 HEA |  | GELINAS
45 | 124 HEA |  | BELLONE |  | Done 2015
46 | 122 HEA |  | ROBERTSON
47 | 120 HEA |  | FREEDMAN
48 | 41 SAGE |  | KUMARI |  | Done 2014
49 | 43 SAGE |  | X
50 | 44 SAGE |  | MAZZARELLA
51 | 42 SAGE |  | DINUCCI |  | Done 2015
52 | 40 SAGE |  | X
53 | 31 KWN |  | HIGGINS
54 | 33 KWN |  | KEEFE
55 | 35 KWN |  | MELLA
56 | 30 KWN |  | SORBO
57 | 32 KWN |  | McNAMARA |  | Done 2014
58 | 34 KWN |  | MURA
59 | 36 KWN |  | MOFFIE |  | Done 2015
60 | 37 KWN |  | KLOPFER |  | Done 2015
61 | 38 KWN |  | TANNER |  | Done 2014
62 | 39 KWN |  | CHONG
63 | 21 IVY |  | KRONICK |  | Done 2014
64 | 23 IVY |  | ODONNELL |  | Done 2014
65 | 26 IVY |  | MILLER |  | Done 2015
66 | 24 IVY |  | JOHNSON |  | Done 2014
67 | 22 IVY |  | JOHNSON | 1708 | 2016
68 | 20 IVY |  | MILLER |  | Done 2013
69 | 10 ASTER |  | FLEISSNER
70 | 12 ASTER |  | COLAVECCHIO
71 | 14 ASTER |  | DEVLIN
72 | 11 ASTER |  | GILLETTE
22 |  |  |  | 16193
17221.2555